## GANTT Fall 2001
GANTT - Magnetohydrodynamic Duck
|  | Days | Days | Duration
Schedule | Start date | Completed | Remaining | (days) | End | Comment
Initial technical discussions | 2001-09-06 | 1 | 1 | 2 | 2001-09-08 | w/ Roylance in 6-202
Preliminary design | 2001-09-07 | 0 | 5 | 5 | 2001-09-12 | present 9/13, 3 PowerPoint slides
Literature review | 2001-09-07 | 0 | 10 | 10 | 2001-09-17 | web, library, texts
Develop analytical methods | 2001-09-13 | 0 | 14 | 14 | 2001-09-27 | MHD effect, flow dynamics, streamlining, battery circuit
Order materials | 2001-09-13 | 0 | 7 | 7 | 2001-09-20 | Fe2O3, Nd-Fe-B powders, locate electromagnet
Mix, calcine, sinter ferrite magnets | 2001-09-25 | 0 | 30 | 30 | 2001-10-25 | WAXD & TGA, ball milling, SEM
Encapsulate & orient Nd magnets | 2001-10-01 | 0 | 40 | 40 | 2001-11-10 | Epoxy? Fabricate electromagnet for powder press
Final design | 2001-10-01 | 0 | 14 | 14 | 2001-10-15 | CAD drawings?
Assemble & test duck drive | 2001-10-10 | 0 | 40 | 40 | 2001-11-19 | Measure Lorentz force, work out steering
Analysis of data | 2001-10-04 | 0 | 50 | 50 | 2001-11-23 | Justify measured and predicted Lorentz force
Fine-tune & optimize duck | 2001-11-20 | 0 | 10 | 10 | 2001-11-30 | Identify & eliminate glitches
Electronic lab notebook | 2001-09-11 | 0 | 85 | 85 | 2001-12-05 | Schedule responsible person, upload to web site
Web page development | 2001-09-11 | 0 | 90 | 90 | 2001-12-10 | Decide on webmaster, but have everyone learn procedure
Develop final web pages | 2001-11-30 | 0 | 10 | 10 | 2001-12-10 | Not too many, but present complete picture
Develop final poster and display items | 2001-12-03 | 0 | 7 | 7 | 2001-12-10 | Check with Kinko, etc., early
Final presentation | 2001-12-10 | 0 | 1 | 1 | 2001-12-11 | Get enough sleep, double-check computer stuff
Formulas:
End = ([Start date]+[Duration])